## Sheet1
Ref | Raised | Closed | Contact | Site | Title | Description | Resolution | Value | Purchase Order
HDT51485 | 2022-03-25 | 2022-04-21 | Lilian Goh | Flat 2.02, 8A Gerrard Street | Glass window broken - quote to repair | Glass window broken - quote to repair | Completed following works on 25/03/2022. Gone to quote for repair | 0 | POHDT51485
HDT52832 | 2022-09-12 | 2022-10-04 | Lilian Goh | Flat 3, 1a Gerrard Place | window is broken | window is broken | Completed following works on 12/09/2022. attended and preparing a quote for replacement | 0 | POHDT52832
HDT52926 | 2022-09-27 | 2022-11-18 | Lilian Goh | Flat 10, Goodwins House, 55-56 St Martins Lane, | Change bulbs for energy efficient ones | Change bulbs for energy efficient ones With the increase in energy prices across the UK, I was wondering if we currently have economic (energy saving) light bulbs currently installed in the flat? If not, can we please get the current light bulbs replaced in the flat with economic ones? | Completed following works on 27/09/2022. | 0 | POHDT52926
HDT53045 | 2022-10-10 | 2022-12-08 | Lilian Goh | Flat 10, Goodwins House, 55-56 St Martins Lane, | With the increase in energy prices across the UK, I was wondering if we currently have economic (energy saving) light bulbs currently installed in the flat? If not, can we please get the current light bulbs replaced in the flat with economic ones? | With the increase in energy prices across the UK, I was wondering if we currently have economic (energy saving) light bulbs currently installed in the flat? If not, can we please get the current light bulbs replaced in the flat with economic ones? 3 -4 pm Tuesday | Completed following works on 28/10/2022. Works gone to quote | 0
HDT54446 | 2023-03-30 | 2023-03-31 | Lilian Goh | Flat 5, 82 Shaftesbury Avenue | MDR/SW/15521 - Re-glazing to window | Re-glazing to window | Completed following works on 31/03/2023. | 435
HDT54751 | 2023-05-11 | 2023-05-17 | Lilian Goh | 28/30 Lisle Street, | Ku Bar Office | Ku Bar Office Repairs to damaged floor leak to the radiator along the hallway | Completed following works on 17/05/2023. | 0 | POHDT54751
HDT55125 | 2023-06-27 | 2023-06-30 | Lilian Goh | Flat 2, 68 Shaftesbury Avenue | The kitchen sink taps aren't attached correctly and most likely need new parts. | The kitchen sink taps aren't attached correctly and most likely need new parts. | Completed following works on 28/06/2023. Works gone to quote | 0
HDT55275 | 2023-07-14 | 2023-07-20 | Lilian Goh | Flat 2.02, 8A Gerrard Street | crack in window is getting bigger | crack in window is getting bigger | Completed following works on 17/07/2023. Works have gone to quote | 0 | POHDT55275
HDT55459 | 2023-08-14 | 2023-08-17 | Lilian Goh | Flat 3.2, 16a Rupert Street , | list of works | list of works hallway Bathroom switch -Ensuite bathroom new latch -reinstate vent covers -window restrictors -new peep hole TENANT VACANTS ON 22ND | Completed following works on 23/08/2023. | 0
HDT55938 | 2023-10-19 | 2023-11-14 | Lilian Goh | Flat 3 Egmont House, 114-118 Shaftesbury Avenue | check front door is working and if it needs to be replaced with a fire door | check front door is working and if it needs to be replaced with a fire door | Completed following works on 20/10/2023. Quotation to be submitted for replacement fire door | 0
HDT56594 | 2024-01-05 | 2024-03-19 | Lilian Goh | Flat 4.2, 28 Lisle Street | list of works | list of works: 1. The wood frame for the mirror cabinet in the bathroom is being destroyed by termites. It's getting into a very bad condition now. I think behind the mirror there might be some problem with the pipes as well because after every shower, it gets soaked from the inside. Can someone take a look at this? Please quote if replacement is required 2. I broke a piece inside the fridge. Because of that, the fridge does not get fully cold. Since I broke this one I am ok paying for the fix, but I would like to know if you have someone specific that I could contact for this kind of problem. Please replace. 3. One of the lights in the living room does not turn on anymore. | Completed following works on 28/03/2024. List of works completed as instructed | 658.46
HDT56607 | 2024-01-08 | 2024-01-09 | Lilian Goh | Flat 5, 32-34 Cranbourn Street | HDT56602 Follow-Up | HDT56602 Follow-Up | Completed following works on 09/01/2024. | 0
HDT57127 | 2024-03-13 | 2024-04-10 | Lilian Goh | Flat 1, 66 Shaftesbury Avenue | HDT57126 Follow-Up - Leaking shower valves. | HDT57126 Follow-Up - Leaking shower valves. | Completed following works on 26/04/2024. Shower repairs gone to quotation | 0
HDT57448 | 2024-04-12 | 2024-04-23 | Lilian Goh | Flat 4, 5 Charlotte Place | list of works | list of works kitchen tap is looseextractor needs to be replacedno hot water in the kitchen sink | Completed following works on 01/05/2024. Attended site to investigate reported issues. The kitchen tap has been tightened back into the correct position. The water heater will be quoted for replacement as this is scaled. | 175
HDT57839 | 2024-05-23 | 2024-05-24 | Lilian Goh | Penthouse, 36 Gerrard Street | measure up for a new cooker | measure up for a new cooker | Completed following works on 26/06/2024. Quotation for replacement to follow | 0
HDT57919 | 2024-06-27 | 2024-08-14 | Lilian Goh | Flat 2.1, 4a Rupert Court | To carry out inter-tenancy checks - For 1st July 2024 | To carry out inter-tenancy checks - For 1st July 2024 Loose toilet seat/blinds/faulty wine cooler living room windows not closing properly Dean to quote for redecs | Completed following works on 13/08/2024. List of inter-tenancy works completed | 1,736.20
HDT57942 | 2024-06-07 | 2024-09-19 | Lilian Goh | Flat 8 Exeter Mansions, 100-112 Shaftesbury Avenue | Inter-tenancy checks | Inter-tenancy checks investigate water stains | Completed following works on 04/09/2024. Carried out inter-tenancy maintenance works as Quick turnaround Carried out preparation works to water damage to ceiling and wall in ensuite and bedroom and decorated Collected replacement kitchen mixer and attended site to replace. Completed pipework modifications and left in full working order Replaced faulty extractor fans for both bathrooms and new smoke detector for hallway and replaced blown lamps Boiler and radiator checks completed batteries changed to thermostat | 1,406.71
HDT58276 | 2024-07-17 | 2024-07-23 | Lilian Goh | Flat 4.2, 28 Lisle Street | Leaking in the bathroom and faulty boiler | Leaking in the bathroom and faulty boiler | Completed following works on 25/07/2024. Attended to inspect damp on bathroom ceiling/wall area, Damp meter reading of below 14% which is acceptable for decorations. Attended site to investigate reported boiler fault. Traced the problem to the pcb which will be collected and replaced Reattended site to replace the main pcb to the boiler. Completed work and left in full working order. | 714.58
HDT58295 | 2024-08-07 | 2024-08-27 | Lilian Goh | Flat 3.1, 76 Shaftesbury Avenue | Inter-tenancy checks | Inter-tenancy checks-to remove hooks on the wall-to remove round shades and replace a new-to measure 3x windows for new double roller blinds-to remove wooden holder-ladder & folded table for Lilian (pls ask if Travis can drop it off to my house on the way home) investigate leak | Completed following works on 27/08/2024. Inter-tenancy maintenance works completed including installing the kitchen cabinet lights and replacement blinds | 2,066.23
HDT58345 | 2024-07-25 | 2024-08-23 | Lilian Goh | Flat 2, 34 Rupert Street | hole in the ceiling | hole in the ceiling Flat hallway to be repaired and painted Fire engineer created the hole for new cables to link to detectors. | Completed following works on 23/08/2024. Hole in the ceiling flat hallway repaired and painted | 288
HDT58357 | 2024-08-22 | 2024-09-16 | Lilian Goh | Flat 2.2, 76 Shaftesbury Avenue | Inter-tenancy checks | Inter-tenancy checks - tenant moves in on 6th | Completed following works on 05/09/2024. Inter-tenancy works completed and redecoration | 1,642.98
HDT58358 | 2024-07-25 | 2024-09-10 | Lilian Goh | Flat 3.2, 76 Shaftesbury Avenue | inter-tenancy checks | inter-tenancy checks | Completed following works on 25/09/2024. Inter-tenancy works completed | 915.5
HDT58366 | 2024-07-26 | 2024-08-13 | Lilian Goh | Flat B, 39 Gerrard Street | Extractor fan not working - Tenant home for access | Extractor fan not working - Tenant home for access | Completed following works on 12/08/2024. Removed/Replaced bathroom fan leaving working | 272.79
HDT58427 | 2024-08-02 | 2024-08-13 | Lilian Goh | Flat 2.3, 16a Rupert Street | EICR (NICEic) | EICR (NICEic) | Completed following works on 12/08/2024. EICR (NICEic) completed | 300
HDT58428 | 2024-08-02 | 2024-09-04 | Lilian Goh | Flat 4.2, 16a Rupert Street | EICR (NICEic) | EICR (NICEic) | Completed following works on 04/09/2024. Carried out EICR | 300
HDT58437 | 2024-08-05 | 2024-09-16 | Lilian Goh | Flat 2, 14 Lisle Street | There is some cracks in the plaster in the corner of the kitchen, under the cupboard above the refrigerator | There is some cracks in the plaster in the corner of the kitchen, under the cupboard above the refrigerator | Completed following works on 10/09/2024. Cracks in the plaster in the corner of the kitchen, under the cupboard above the refrigerator repaired and redecorated | 265
HDT58440 | 2024-08-05 | 2024-08-16 | Lilian Goh | 4 Dansey Place, | fridge seal need to be refitted | fridge seal need to be refitted | Completed following works on 23/08/2024. Supplied and fitted new fridge seal | 370.04
HDT58443 | 2024-08-06 | 2024-08-14 | Lilian Goh | Flat 2.1, 4a Rupert Court | All ceilings to be decorated except hallway | All ceilings to be decorated except hallwayEnsuite bathroom - to remove moldy silicone and apply new inside/outside of the shower door and corners. Please check bathroom 2 if it it's moldy.Gas check - to adjust thermo to a comfortable temperature. To replace missing towel rails metal cap - both bathroomsWine chiller - a small container secured with cello tape on top shelf to be removed. Not sure what is that for? missing fridge shelf | Completed following works on 23/08/2024. List of works completed Attended site to replace the towel rail brackets in both bathrooms. Stripped and re-packed the towel rail valves which were found leaking. The towel rail in the ensuite also required a replacement head cut out mastic to outer and inner of front of shower sliding door and replaced in white. Cleaned out joint line in kitchen splash back, cleaned and applied white mastic to seal. Repaired kitchen light replace dimmer switch and replaced 2 broken sockets Redecoration of ceilings completed Replaced missing fridge shelf | 1,463.12
HDT58458 | 2024-08-06 | 2024-08-13 | Lilian Goh | Flat 2, 24a Wardour Street | List of works - For Tuesday 13th August at 11am - Cleaner to give access | List of works - For Tuesday 13th August at 11am - Cleaner to give access To reinstate the wall skirting outside the bathroom To install a small pull handle door rim | Completed following works on 12/08/2024. List of works completed Mastic to outside of shower, Threshold bar to bathroom tiles, Reinstated skirting and made good, Pull type escutcheon to main door lock. | 296.9
HDT58469 | 2024-08-07 | 2024-09-10 | Lilian Goh | 3rd Floor, 24a Newport Court | bathroom ceiling needs painting | bathroom ceiling needs painting | Completed following works on 09/09/2024. Carried out complete redecoration of bathroom ceiling as instructed | 498
HDT58470 | 2024-08-22 | 2024-09-05 | Lilian Goh | 4th Floor, 62 Shaftesbury Avenue | Inter-tenancy checks | Inter-tenancy checksCheck wardrobe sliding cupboard doors Smoke seals required and to adjust door latch | Completed following works on 05/09/2024. Carried out ITC works | 628.92
HDT58474 | 2024-08-08 | 2024-08-21 | Lilian Goh | Flat 1, 27 Wardour Street | PAT test | PAT test | Completed following works on 21/08/2024. Carried out PAT testing and issued certificate to client on completion | 85
HDT58475 | 2024-08-08 | 2024-08-21 | Lilian Goh | Flat 2, 27 Wardour Street | PAT test | PAT test | Completed following works on 21/08/2024. Carried out PAT testing and issued certificate to client on completion | 85
HDT58476 | 2024-08-08 | 2024-08-21 | Lilian Goh | Flat 3 , 27 Wardour Street | PAT test | PAT test | Completed following works on 21/08/2024. Carried out PAT testing and issued certificate to client on completion | 85
HDT58496 | 2024-08-09 | 2024-08-19 | Lilian Goh | Flat 3 Nassau House, 120-124 Shaftesbury Avenue | Bristles required to Flat door | Bristles required to Flat door | Completed following works on 19/08/2024. Supply and fit door Bristles to Flat door | 145
HDT58497 | 2024-08-09 | 2024-08-19 | Lilian Goh | Flat 1, 66 Shaftesbury Avenue | adjust door closer | adjust door closer | Completed following works on 19/08/2024. Adjust door Closer and leave all in working order. | 95
HDT58498 | 2024-08-09 | 2024-08-23 | Lilian Goh | Flat 1.1, 66 Shaftesbury Avenue | missing door seals | missing door seals | Completed following works on 23/08/2024. Smoke seals fitted around apartment entrance door as required | 214.15
HDT58499 | 2024-08-15 | 2024-08-19 | Lilian Goh | Flat 1.2, 66 Shaftesbury Avenue | door seal is missing and door lock issue - Management keys for access | door seal is missing The tenant also noticed I noticed the door has some issues locking/unlocking and opening | Completed following works on 19/08/2024. Multipoint lock and keep adjustments to main apartment door, tested, Smoke seals fitted to main door frame | 210.56
HDT58500 | 2024-08-09 | 2024-08-20 | Lilian Goh | 36-40 Rupert Street , | All Flats (smoke seals & intumescent strips & door bristles) | All Flats (smoke seals & intumescent strips & door bristles) | Completed following works on 20/08/2024. H&S Works carried out to metal apartment doors, Draught seals (bristles) fitted where required. | 247.36
HDT58501 | 2024-08-09 | 2024-08-19 | Lilian Goh | 58 Shaftesbury Avenue , | Flats 1, 2 and 3 | Flats 1, 2 and 3 Bristle brushes required to Flats 1 and 2 Adjust door closer to click shut in Flat 3 | Completed following works on 28/08/2024. Installed bristle brushes to Flats 1, 2 & 3 and adjusted door closer to Flat 3 | 275.69
HDT58503 | 2024-08-09 | 2024-08-28 | Lilian Goh | 34 Rupert Street , | Flat 2 & 4 | Flat 2 & 4 Bristle brush required to both flats and adjust closer to click shut | Completed following works on 20/08/2024. Supplied and installed bristles to flat 2 and 4 doors Adjust door closers to both flats leaving working | 210.96
HDT58504 | 2024-08-09 | 2024-09-04 | Lilian Goh | Flat 1, 27 Lisle Street | door bristle required | door bristle required | Completed following works on 04/09/2024. Fit new door bristle strip /draft excluder to bottom of door | 104.98
HDT58505 | 2024-08-09 | 2024-08-22 | Lilian Goh | 39 Wardour Street , | All flats | All flats bristles on door and adjust closer to click shut | Completed following works on 22/08/2024. Attended and fitted draught seals to apartment door and adjusted door closer leaving working | 153.02
HDT58506 | 2024-08-09 | 2024-08-28 | Lilian Goh | 2nd/3rd Floor Flat , 5b Rupert Court | Bristles required to door | Bristles required to door | Completed following works on 20/08/2024. Supplied and installed new bristles strip to door | 110
HDT58509 | 2024-08-12 | 2024-08-13 | Lilian Goh | Flat B, 24 Rupert Street | 5B Rupert Court | list of works fire strips for 2 doors chrome beading shower outlet cover | Completed following works on 13/08/2024. List of works completed as instructed | 320.47
HDT58511 | 2024-08-12 | 2024-08-13 | Lilian Goh | 2nd Floor, 4 Gerrard Street | no hot water | no hot water | Completed following works on 12/08/2024. Attended site to investigate reported hot water fault. Had to re-pressurise the boiler, checked the system where possible but could find no leaks. Put the boiler into a venting cycle and left in full working order | 175
HDT58517 | 2024-08-12 | 2024-08-13 | Lilian Goh | Flat 3.1, 4a Rupert Court | flush not working | flush not working | Completed following works on 13/08/2024. Attended site to investigate toilet flush problem. Removed flush plate and found that the pneumatic tube was damaged. The tube was cut back and the syphon rebuilt, leaving in full working order | 175
HDT58524 | 2024-08-13 | 2024-08-19 | Lilian Goh | 8a Gerrard Street , | check all riser cupboards to ensure the sockets are safe | check all riser cupboards to ensure the sockets are safe | Completed following works on 15/08/2024. Check all sockets in riser cupboard and report back that all equipment plugged into sockets belong to tenants | 95
HDT58525 | 2024-08-13 | 2024-08-19 | Lilian Goh | 11a Gerrard Street , | check all riser cupboards to property to ensure sockets are safe | check all riser cupboards to property to ensure sockets are safe | Completed following works on 15/08/2024. Check all sockets in riser cupboard and PAT test landlord equipment plugged in | 95
HDT58533 | 2024-08-14 | 2024-08-19 | Lilian Goh | 21a Newport Court, | clear the gully and flush thoroughly with disinfectant. | clear the gully and flush thoroughly with disinfectant. Hi Greg, can you please inform your tenant to leave the room doors unlocked. | Completed following works on 16/08/2024. Clear gulley and flushed through. Used disinfectant | 195
HDT58535 | 2024-08-14 | 2024-09-19 | Lilian Goh | 14 Lisle Street , | MDR/MDR/16402 - Removal and Disposal of Planters: | Removal and Disposal of Planters: | Completed following works on 19/09/2024. Removal and Disposal of Planters as per quotation. | 1,485.00
HDT58536 | 2024-08-16 | 2024-08-30 | Lilian Goh | Flat 3.1, 76 Shaftesbury Avenue | de-humidifier and investigate leak | de-humidifier and investigate leak New tenant is moving in on the 26th Aug. Leak was discovered last week. Travis cleared the gulley but looking at the stain, the damp is below where the sockets are. This job is not part of ITC but were raised as additional leak investigation therefore please arrange for this to be looked at asap. This Flat need to be ready by Friday 23rd. | Completed following works on 29/08/2024. Carried out camera survey and found leak coming from ball-valve in loft replaced ball-valve with new and left all watertight Hired dehumidifier as instructed and off hired once area dry | 335
HDT58538 | 2024-08-14 | 2024-08-14 | Lilian Goh | 2nd Floor, 21a Newport Court | the plug for the microwave in the kitchen is faulty and not working. | the plug for the microwave in the kitchen is faulty and not working. | Completed following works on 14/08/2024. Replaced faulty socket for microwave leaving working | 105
HDT58539 | 2024-08-14 | 2024-08-14 | Lilian Goh | Flat 1 Exeter Mansions, 100-112 Shaftesbury Avenue | tidy cables up in electrical cupboard | tidy cables up in electrical cupboard | Completed following works on 14/08/2024. Tidied cables up in electrical cupboard as instructed | 95
HDT58543 | 2024-08-15 | 2024-08-27 | Lilian Goh | Flat B, 24 Rupert Street | 2No replacement blinds - Flat B, 5B Rupert Court | 2No replacement blinds | Completed following works on 27/08/2024. 2No replacement blinds supplied and fitted | 430
HDT58557 | 2024-08-16 | 2024-09-16 | Lilian Goh | Flat 1 Egmont House, 114-118 Shaftesbury Avenue | TO carry out Inter-tenancy checks - For 2nd September | TO carry out Inter-tenancy checks - For 2nd September | Completed following works on 16/09/2024. Inter-tenancy works completed and list sent to client | 335
HDT58562 | 2024-08-16 | 2024-08-19 | Lilian Goh | Flat 2.1, 28 Lisle Street | Toilet continually flushing - to collect keys for access but buzz first. | Toilet continually flushing - to collect keys for access but buzz first. | Completed following works on 16/08/2024. Remove and replaced faulty ball valve. | 205
HDT58563 | 2024-08-16 | 2024-08-16 | Lilian Goh | Flat 5.1, 16a Rupert Street | Blocked door - laundry area - Tenant home until 5pm today | Blocked door - laundry area - Tenant home until 5pm today The tenant can provide access anytime till 5pm today. Please buzz on the door and tell her that Lilian arranged. The tenant reported: Just a minor issue; I used the washing machine, and closed the door to the small room in the pantry area. The washing machine moved during use, and has blocked the door | Completed following works on 16/08/2024. Main door opened and washing machine reinstated back into position. | 103.04
HDT58564 | 2024-08-16 | 2024-08-29 | Lilian Goh | 1st Floor, 76 Shaftesbury Avenue | 1st Floor Travel Agent Office (right side) - office 2nd door handle is broken | 1st Floor Travel Agent Office (right side) - - office 2nd door handle is broken | Completed following works on 29/08/2024. Supplied and fitted new door handle to match existing, leaving in full working order | 304.68
HDT58567 | 2024-08-19 | 2024-08-19 | Lilian Goh | 3rd Floor Flat, 21A Newport Court | Bathroom light not working: | Bathroom light not working: | Completed following works on 19/08/2024. Replaced bathroom pull cord switch. | 107.5
HDT58569 | 2024-08-19 | 2024-08-19 | Lilian Goh | Flat 4.1, 28 Lisle Street | No heating or hot water: | No heating or hot water: | Completed following works on 19/08/2024. Gas valve on boiler not working repaired and left working | 175
HDT58574 | 2024-08-20 | 2024-08-23 | Lilian Goh | Flat 3.1, 28 Lisle Street | The oven light need to be replaced - For Wednesday 21st August at 2pm - tenant home | The oven light need to be replaced - For Wednesday 21st August at 2pm - tenant home | Completed following works on 21/08/2024. Replaced blown lamp in oven leaving working | 113.97
HDT58577 | 2024-08-20 | 2024-08-29 | Lilian Goh | Flat 1, 21a Newport Court | Washing machine not working, the spin cycle is not spinning effectively so washing come out wet | Washing machine not working, the spin cycle is not spinning effectively so washing come out wet | Completed following works on 28/08/2024. Spin cycle repaired on washing machine leaving working | 180
HDT58581 | 2024-08-20 | 2024-09-05 | Lilian Goh | 4th Floor, 62 Shaftesbury Avenue | 4th Floor, Flat 1 - Electric meter readings - FOR 5TH SEPTEMBER | 4th Floor, Flat 1 - Electric meter readings - FOR 5TH SEPTEMBER Can you please arrange for Alan to send me the picture of Electric meter readings. It must be taken on the 5th. Alan, please ask Eva for the keys to Leon. I do not want the inventory clerk to access Leon. You know this venue better. | Completed following works on 05/09/2024. Attended site and took meter readings as requested. Please see attached photos on job ticket report. | 95
HDT58582 | 2024-08-20 | 2024-08-21 | Lilian Goh | 25 Wardour Street, | No lights in the common parts | No lights in the common parts | Completed following works on 20/08/2024. Reset RCD leaving lighting in full working order | 95
HDT58585 | 2024-08-21 | 2024-08-29 | Lilian Goh | 1st Floor, 62 Shaftesbury Avenue | PAT test only | PAT test only | Completed following works on 29/08/2024. PAT testing completed and certificate sent to client | 85
HDT58606 | 2024-08-22 | 2024-08-29 | Lilian Goh | Flat 1, 94 Shaftesbury Avenue | fridge not cooling | fridge not cooling Despite our team inspecting the appliance, including the fuses and functionality, it appears that the refrigerator is not cooling properly. Regardless of the cooling setting (from 1 to 5), the temperature remains insufficient (doesn't cool) to preserve food, leading to spoilage washer/dryer not drying | Completed following works on 28/08/2024. Both fridge/freezer and washer/dryer repaired and left in full working order | 286.78
HDT58607 | 2024-08-22 | 2024-08-22 | Lilian Goh | Flat 2, 11a Gerrard Street | clear gutter from bathroom window | clear gutter from bathroom window | Completed following works on 22/08/2024. Attended and tried to source where fruit flies are entering, Cleared outside bathroom window gully area, Left tenant with fly killer spray and recommend filters being replaced in apartment extractor system. Photos of extractor for reference. | 109.23
HDT58608 | 2024-08-22 | 2024-09-10 | Lilian Goh | Flat 3.2, 16a Rupert Street | redecs around living window once new window is replaced. | redecs around living window once new window is replaced. | Completed following works on 09/09/2024. Made good and carried out full redecoration around living room windows as instructed | 485
HDT58613 | 2024-08-22 | 2024-08-22 | Lilian Goh | 58 Shaftesbury Avenue , | main front door closer needs adjusting so door closes | main front door closer needs adjusting so door closes | Completed following works on 22/08/2024. Attended and adjusted door closer to stop door slamming and to close positively. | 95
HDT58632 | 2024-08-28 | 2024-09-17 | Lilian Goh | Flat 2, 68 Shaftesbury Avenue | list of works | list of works: Washing Machine: The washing machine produces an excessive amount of noise when spinning. It vibrates significantly, causing the adjacent cupboard to shake. Additionally, the machine generates hot steam, which has unfortunately led to damage on the cupboard. Dishwasher: The dishwasher is difficult to open and close due to an obstruction caused by the cupboard layer beneath it. This has made the dishwasher almost unusable. Bathroom Door: The bathroom door is quite noisy and squeaks whenever it is closed. Shower Door: The shower door is not properly latched on and needs to be fixed to prevent any potential accidents. Toilet Seat: The hinge on the toilet seat is broken and requires repair. | Completed following works on 17/09/2024. Washing machine repaired and left working Overhauled dishwasher, bathroom door, shower door and toilet seat | 291.08
HDT58680 | 2024-09-02 | 2024-09-03 | Lilian Goh | Flat 1a, Cooper House 82/88 Shaftesbury Avenue | screw to be tightened on boiler cupboard | screw to be tightened on boiler cupboard to screw it back to the wall to stop rodents | Completed following works on 03/09/2024. Attended and refitted cast iron radiator support bracket as instructed by tenant. | 95
HDT58682 | 2024-09-02 | 2024-09-20 | Lilian Goh | Flat 1, 27 Lisle Street | list of works | list of works:Issue 1: My shelves in my bathroom cabinet have fallen down. I have tried to fix myself, but I am struggling. Issue 2: I believe there is a small crack in my washing machine causing water leak out onto the floor, it has been like this since Saturday so I have turned it off.My dog Will be at work with me. I give you permission to give access, anytime/day is fine. | Completed following works on 20/09/2024. Collection of keys and attended above property, Found glass shelf brackets in bathroom cabinet to be broken, managed to refit two of the three shelves, ordered 4No new special order brackets Returned to site once in stock, and supplied and fitted new brackets to shelves in bathroom Appliance engineer attend and the seal clamp was refitted; the engineer advised the leak occurs due to too much foam - the engineer advised the tenant to change the washing detergent they are using, as when the engineer tested the appliance without powder there was no leak, | 478.23
HDT58697 | 2024-09-03 | 2024-09-04 | Lilian Goh | Flat 2.1, 16a Rupert Street | leak from radiator | leak from radiator - boiler issue | Completed following works on 03/09/2024. Attended site to investigate reported radiator leak. Checked all radiators but found the right hand bedroom radiator at fault. Rectified leak, re-pressurised the system and put the boiler into a vent cycle. Left in full working order on completion | 175
HDT58734 | 2024-09-06 | 2024-09-10 | Lilian Goh | Flat 2, 24a Newport Court | Kitchen Tap keeps squirting water from joint in the fitting | Kitchen Tap keeps squirting water from joint in the fitting | Completed following works on 09/09/2024. Attended site to re-fit kitchen tap spout and to leave in working order. | 95
HDT58753 | 2024-09-10 | 2024-09-10 | Lilian Goh | Flat 3.2, 16a Rupert Street | Mastic sealant replacement and tap repairs | Mastic sealant replacement and tap repairs | Completed following works on 10/09/2024. Supplied and fitted 2No new x cartridges to taps, commissioned, tested and left in full working order Racked out and replaced mastic sealant and sealed | 410.77
HDT58754 | 2024-09-10 | 2024-09-16 | Lilian Goh | Flat 8 Exeter Mansions, 100-112 Shaftesbury Avenue | list of works | list of works: secure hinge to washer dryer door Remove hooks(kitchen wall) Kitchen sink reseal the bottom between sink and worktop | Completed following works on 11/09/2024. List of works completed | 95
HDT58758 | 2024-09-10 | 2024-09-12 | Lilian Goh | 9a Little Newport Street , | List of works: | List of works: Kitchen door handle loose to top floor Door closer issue to the kitchen door Inspect door to see if it needs intumescent seals To supply and fit new kitchen fire blanket To supply and fit restrictor to kitchen window To remove tall ladder from site | Completed following works on 11/09/2024. Kitchen door handle refixed Overhauled door closer to the kitchen door Fitted new kitchen fire blanket Fitted restrictor to kitchen window Removed tall ladder from site | 255
HDT58759 | 2024-09-10 | 2024-09-11 | Lilian Goh | Flat 2, 24a Newport Court | electric radiator in room 2 doesnt work | electric radiator in room 2 doesnt work | Completed following works on 11/09/2024. Reset electric heater in bedroom and left in full working | 95
HDT58767 | 2024-09-11 | 2024-09-12 | Lilian Goh | 9a Little Newport Street , | Cupboard in basement - smell of gas - report to Hairdressers | Cupboard in basement - smell of gas - report to Hairdressers | Completed following works on 11/09/2024. Attended site investigate reported gas smell. Isolated gas due to the meter condition, gas meter was found to be leaking and corroded, issued warning notice and informed client to report to their gas supplier. | 175
HDT58768 | 2024-09-11 | 2024-09-19 | Lilian Goh | Flat 4 Egmont House, 114-118 Shaftesbury Avenue | Tenant has reported a shower issue | Tenant has reported a shower issue | Completed following works on 20/09/2024. Attended site to investigate shower issue. Found that the on/off cartridge is letting by and because of the age of the shower a quotation for a replacement unit will be submitted | 95
HDT58773 | 2024-09-12 | 2024-09-17 | Lilian Goh | 9a Little Newport Street , | To be in attendance at 4pm today with gas company who are changing the meter | To be in attendance at 4pm today with gas company who are changing the meter | Completed following works on 16/09/2024. Collected keys and attended the hairdressers to meet the gas supplier. Waited on-site until the decision was made to re-attend following the new meter installation Returned to site to test gas pipework following new meter installation. Reinstated boiler on completion. | 335
HDT58774 | 2024-09-12 | 2024-09-13 | Lilian Goh | 2/3rd Floor Flat , 6 Gerrard Street | Top floor bedroom, door handle loose and also main front door to property stiff to open - Keys for access | Top floor bedroom, door handle loose and also main front door to property stiff to open - Keys for access | Completed following works on 12/09/2024. Retightened lock/handle to bedroom door. All secure Also refixed lock to door All ok | 95
HDT58783 | 2024-09-13 | 2024-09-19 | Lilian Goh | Flat 4, 2a Gerrard Place | Shower door wheels issue - management keys for access - For Monday 16th September | Shower door wheels issue - management keys for access - For Monday 16th September | Completed following works on 18/09/2024. Attended site to investigate shower door brackets. Removed existing lower brackets and collected universal brackets from suppliers. Fitted lower brackets, re-aligned doors, greased and left in full working order | 310
HDT58784 | 2024-09-13 | 2024-09-17 | Lilian Goh | Flat 3.3, 16a Rupert Street | EICR (NICEic) - For Monday 16th September - Tenant home for access | EICR (NICEic) - For Monday 16th September - Tenant home for access | Completed following works on 16/09/2024. EICR (NICEic) completed | 300
HDT58787 | 2024-09-13 | 2024-09-17 | Lilian Goh | Flat 1.4, 16a Rupert Street | EICR (NICEic) - For Monday 16 September at 1pm - Tenant home | EICR (NICEic) - For Monday 16 September at 1pm - Tenant home | Completed following works on 16/09/2024. EICR (NICEic) completed | 300
HDT58788 | 2024-09-13 | 2024-09-17 | Lilian Goh | Flat 2, 36-40 Rupert Street | Window issues and heating control - For Monday 16th September at 1pm - Tenant home for access | Window issues and heating control - For Monday 16th September at 1pm - Tenant home for access 1. The windows seem to be stuck and don’t open, which could be a concern. Could we arrange to have them fixed? The air quality in the flat was pretty poor as there’s no ventilation opportunities. 2. I couldn’t operate the thermostat for the heating system—it appears to be locked, or perhaps I’m not using it correctly. Could you advise on how to use it? | Completed following works on 16/09/2024. Freed windows where accessible, further works will be required to the windows via external elevation Attended site to investigate heating controls and to instruct tenant how to use. Found the controls to be salus which are an old type. Replacement controls have been quoted. | 270
HDT58791 | 2024-09-16 | 2024-09-17 | Lilian Goh | Flat 2, 1a Gerrard Place | To investigate leak - For today - Please ring Adriana to assist with access. 07340565962 | To investigate leak - For today - Please ring Adriana to assist with access. 07340565962 | Completed following works on 16/09/2024. Attended site to investigate reported leak from flat 2. Ran all services but could find no cause. There was some surface water on the bathroom floor which could have been the cause, travelling underneath the tiles between floor and shower tray. We may need to re-attend if fault persists | 175
HDT58797 | 2024-09-16 | 2024-09-18 | Lilian Goh | Flat 2, 58a Shaftesbury Avenue | No heating in Flat 2 - For Tuesday 17th September - keys for access | For Tuesday 17th September - keys for access No heating in Flat 2Mike knows what times i like the heating to come on and off at. 6am to 10am and 6pm to 2am please | Completed following works on 17/09/2024. Attended site, drained down heating and removed the system strainer, cleaned and re-fitted. Vented system and carried out checks to the heating and hot water controls to confirm correct operation. Left in full working order | 255
HDT58799 | 2024-09-16 | 2024-09-17 | Lilian Goh | Flat 1 Exeter Mansions, 100-112 Shaftesbury Avenue | Leak into Flat 1 - think it's sewage water from Flat 3. - Collect keys for Flat 1 and 3 for access | Leak into Flat 1 - think it's sewage water from Flat 3. - Collect keys for Flat 1 and 3 for access | Completed following works on 16/09/2024. No leak found. Checked both bathrooms and checked flat 3 for blockages. Only thing found was in flat 1 the first bathroom was discolouration around some light fittings. Looks like where someone has stain blocked or used a slight off white paint, reported back findings | 95
HDT58802 | 2024-09-17 | 2024-09-19 | Lilian Goh | 9a Little Newport Street , | Heating not working - Keys for access | Heating not working The guys in the room on the first floor have been trying to get it going but without success To set up heating Daily 6am to 10am and 6pm to 2am. | Completed following works on 18/09/2024. Attended site to investigate heating controls. Found that the batteries required replacing to the controller. Collected batteries, paired controls and confirmed correct operation | 159.48
HDT58805 | 2024-09-17 | 2024-09-19 | Lilian Goh | 21a Wardour Street , | CBRE office - to ease the kitchen door closer. It's slamming too hard. | CBRE office - to ease the kitchen door closer - It's slamming too hard. | Completed following works on 19/09/2024. Replacement door closer supplied and fitted to kitchen door, adjusted to suit, leaving in full working order | 228.03
HDT58815 | 2024-09-18 | 2024-09-18 | Lilian Goh | 26 Rupert Street , | Emergency call-out, out of hours - Break in | Emergency call-out, out of hours - Break in | Completed following works on 18/09/2024. Attended emergency call-out, out of hours to break-in Changed locks for new and temporary fixing of broken door. | 300
HDT58823 | 2024-09-18 | 2024-09-19 | Lilian Goh | Flat 1.3, 16a Rupert Street | Bathroom window is stuck and can't be closed - Tenant can provide access from 10am on Thursday 19th September | Bathroom window is stuck and can't be closed - Tenant can provide access from 10am on Thursday 19th September | Completed following works on 19/09/2024. Refixed secondary glazing to bathroom window | 95